## Approved 2026
Protection Renewal Programme 2026-2035, approved by the Board 19 March 2026
Scheme | Substation code | Substation | Region | Scope | Commissioning month
PRP-001 | DS-001 | Cedar Road | Central | Feeder protection upgrade, 4 bays, IEC 61850 station bus | Jan 2027
PRP-002 | DS-127 | Kingsmount | Central | Replace feeder protection, 4 bays | Feb 2027
PRP-003 | DS-080 | Spring Ridge | South | Replace VPR-340 feeder relays (6) and RTU | Mar 2027
PRP-004 | TS-025 | Brant Falls | North | Protection and control panel replacement (6 feeder bays) | Apr 2027
PRP-005 | TS-058 | Elm Point | North | P&C rebuild with new control building (1 bays) | May 2027
PRP-006 | DS-119 | Cedar Junction | North | P&C rebuild with new control building (1 bays) | Jun 2027
PRP-007 | DS-014 | Cedarbrook | Central | Protection and control panel replacement (2 feeder bays) | Jul 2027
PRP-008 | DS-054 | Long River | North | Protection and control panel replacement (4 feeder bays) | Aug 2027
PRP-009 | DS-134 | Mossfield | North | Replace feeder protection, 2 bays | Sep 2027
PRP-010 | DS-046 | Hawkford | North | Replace VPR-340 feeder relays (3) and RTU | Oct 2027
PRP-011 | DS-120 | Lakewood | South | Feeder protection upgrade, 3 bays, IEC 61850 station bus | Nov 2027
PRP-012 | DS-128 | Rock Bay | Central | Feeder protection upgrade, 4 bays, IEC 61850 station bus | Dec 2027
PRP-013 | DS-016 | Long Road | South | Feeder protection upgrade, 2 bays, IEC 61850 station bus | Jan 2028
PRP-014 | DS-002 | West River | North | Replace VPR-340 feeder relays (5) and RTU | Feb 2028
PRP-015 | DS-064 | Kettle Bridge | North | Replace VPR-340 feeder relays (5) and RTU | Mar 2028
PRP-016 | TS-110 | Red Creek | Central | Replace VPR-340 feeder relays (7) and RTU | Apr 2028
PRP-017 | DS-106 | Willow Bridge | Central | Protection and control panel replacement (9 feeder bays) | May 2028
PRP-018 | DS-069 | Sand Landing | Central | Protection and control panel replacement (6 feeder bays) | Jun 2028
PRP-019 | DS-122 | Ash Bridge | South | Feeder protection upgrade, 8 bays, IEC 61850 station bus | Jul 2028
PRP-020 | DS-033 | Elmdale | North | Replace VPR-340 feeder relays (4) and RTU | Aug 2028
PRP-021 | DS-075 | Ash Creek | North | Replace VPR-340 feeder relays (1) and RTU | Sep 2028
PRP-022 | DS-104 | Stone Mills | South | Feeder protection upgrade, 6 bays, IEC 61850 station bus | Nov 2028
PRP-023 | TS-138 | Kingston | Central | Replace feeder protection, 8 bays | Dec 2028
PRP-024 | DS-028 | Silver Ridge | North | Replace feeder protection, 2 bays | Jan 2029
PRP-025 | DS-115 | Crow Junction | Central | Feeder protection upgrade, 3 bays, IEC 61850 station bus | Feb 2029
PRP-026 | DS-045 | Rock Hill | South | Feeder protection upgrade, 4 bays, IEC 61850 station bus | Mar 2029
PRP-027 | DS-108 | Whitefield | South | Protection and control panel replacement (2 feeder bays) | Apr 2029
PRP-028 | DS-035 | Clearton | South | Feeder relay replacement, 7 bays, with panel rewiring | May 2029
PRP-029 | DS-029 | Bear River | Central | Feeder protection upgrade, 4 bays, IEC 61850 station bus | Jun 2029
PRP-030 | DS-022 | Wolfford | North | Replace feeder protection, 6 bays | Jul 2029
PRP-031 | TS-090 | Fox Mills | North | Protection and control panel replacement (7 feeder bays) | Aug 2029
PRP-032 | DS-019 | Glen Bay | North | Replace feeder protection, 4 bays | Sep 2029
PRP-033 | DS-068 | Iron Corners | South | Feeder relay replacement, 3 bays, with panel rewiring | Oct 2029
PRP-034 | DS-036 | Whitedale | Central | P&C rebuild with new control building (8 bays) | Nov 2029
PRP-035 | DS-139 | Birch Landing | South | Feeder protection upgrade, 8 bays, IEC 61850 station bus | Dec 2029
PRP-036 | TS-039 | Deerwood | North | Replace feeder protection, 1 bays | Jan 2030
PRP-037 | DS-131 | Springwood | Central | Feeder protection upgrade, 5 bays, IEC 61850 station bus | Feb 2030
PRP-038 | DS-038 | Whitemount | North | Feeder protection upgrade, 4 bays, IEC 61850 station bus | Mar 2030
PRP-039 | DS-126 | Long Falls | South | P&C rebuild with new control building (7 bays) | Apr 2030
PRP-040 | DS-087 | Wolf River | North | Feeder protection upgrade, 3 bays, IEC 61850 station bus | May 2030
PRP-041 | DS-084 | Mill Landing | Central | Replace feeder protection, 3 bays | Jun 2030
PRP-042 | DS-067 | Hawk Hill | South | Protection and control panel replacement (6 feeder bays) | Jul 2030
PRP-043 | DS-020 | Heronwood | North | Feeder relay replacement, 7 bays, with panel rewiring | Sep 2030
PRP-044 | DS-011 | Port Landing | South | Replace feeder protection, 7 bays | Oct 2030
PRP-045 | DS-021 | Rock Point | North | Feeder protection upgrade, 1 bays, IEC 61850 station bus | Nov 2030
PRP-046 | DS-082 | Wolf Landing | Central | Replace feeder protection, 7 bays | Dec 2030
PRP-047 | DS-026 | Hawk Junction | Central | Replace VPR-340 feeder relays (7) and RTU | Jan 2031
PRP-048 | DS-140 | Elmfield | South | Feeder protection upgrade, 6 bays, IEC 61850 station bus | Feb 2031
PRP-049 | DS-114 | Glenhurst | Central | Replace VPR-340 feeder relays (9) and RTU | Mar 2031
PRP-050 | DS-061 | Spring River | Central | Feeder protection upgrade, 4 bays, IEC 61850 station bus | Apr 2031
PRP-051 | DS-062 | Oakton | North | Replace VPR-340 feeder relays (7) and RTU | May 2031
PRP-052 | TS-081 | Rockwood | North | P&C rebuild with new control building (4 bays) | Jun 2031
PRP-053 | DS-010 | Hawk Bay | Central | Protection and control panel replacement (5 feeder bays) | Jul 2031
PRP-054 | DS-109 | Fernwood | Central | Replace feeder protection, 5 bays | Aug 2031
PRP-055 | DS-107 | Long Ridge | North | Feeder relay replacement, 7 bays, with panel rewiring | Sep 2031
PRP-056 | DS-116 | Rockmount | South | Replace VPR-340 feeder relays (6) and RTU | Oct 2031
PRP-057 | DS-137 | Bear Landing | South | Protection and control panel replacement (5 feeder bays) | Nov 2031
PRP-058 | DS-117 | Willowhurst | Central | Feeder protection upgrade, 9 bays, IEC 61850 station bus | Dec 2031
PRP-059 | DS-112 | Sandfield | North | Feeder relay replacement, 2 bays, with panel rewiring | Jan 2032
PRP-060 | DS-047 | Cedar Ridge | South | Protection and control panel replacement (7 feeder bays) | Feb 2032
PRP-061 | DS-070 | Moss Creek | South | P&C rebuild with new control building (6 bays) | Mar 2032
PRP-062 | DS-095 | Ashhurst | South | Feeder relay replacement, 6 bays, with panel rewiring | Apr 2032
PRP-063 | DS-032 | Spring Corners | North | Protection and control panel replacement (8 feeder bays) | Jun 2032
PRP-064 | DS-124 | Cedar Mills | North | Protection and control panel replacement (8 feeder bays) | Jul 2032
PRP-065 | DS-135 | Fern Point | North | Protection and control panel replacement (5 feeder bays) | Aug 2032
PRP-066 | DS-007 | Stone Bridge | South | P&C rebuild with new control building (4 bays) | Sep 2032
PRP-067 | DS-111 | Cedar Bridge | Central | Feeder protection upgrade, 8 bays, IEC 61850 station bus | Oct 2032
PRP-068 | DS-125 | Glenfield | South | Replace VPR-340 feeder relays (7) and RTU | Nov 2032
PRP-069 | DS-043 | Moss Road | North | P&C rebuild with new control building (2 bays) | Dec 2032
PRP-070 | DS-071 | Sugarford | South | Feeder relay replacement, 3 bays, with panel rewiring | Jan 2033
PRP-071 | DS-041 | Brant Ridge | North | P&C rebuild with new control building (7 bays) | Feb 2033
PRP-072 | DS-096 | Iron Point | South | Feeder protection upgrade, 5 bays, IEC 61850 station bus | Mar 2033
PRP-073 | DS-094 | Willowwood | North | Protection and control panel replacement (3 feeder bays) | Apr 2033
PRP-074 | DS-004 | Otter Landing | South | Replace VPR-340 feeder relays (3) and RTU | May 2033
PRP-075 | DS-101 | Silverford | Central | Feeder relay replacement, 4 bays, with panel rewiring | Jun 2033
PRP-076 | DS-050 | Maplebrook | North | Protection and control panel replacement (4 feeder bays) | Jul 2033
PRP-077 | TS-100 | Silver Falls | North | Feeder protection upgrade, 4 bays, IEC 61850 station bus | Aug 2033
PRP-078 | DS-063 | Heron Falls | South | Protection and control panel replacement (1 feeder bays) | Sep 2033
PRP-079 | DS-030 | Millbrook | North | P&C rebuild with new control building (5 bays) | Oct 2033
PRP-080 | DS-027 | North Hill | Central | Protection and control panel replacement (9 feeder bays) | Nov 2033
PRP-081 | DS-005 | Silver River | Central | Feeder protection upgrade, 8 bays, IEC 61850 station bus | Dec 2033
PRP-082 | DS-059 | Clear Point | North | Feeder relay replacement, 2 bays, with panel rewiring | Jan 2034
PRP-083 | TS-098 | Redwood | North | Protection and control panel replacement (6 feeder bays) | Feb 2034
PRP-084 | DS-053 | Hawk Mills | North | Replace feeder protection, 3 bays | Apr 2034
PRP-085 | DS-018 | Sandville | North | Feeder protection upgrade, 2 bays, IEC 61850 station bus | May 2034
PRP-086 | DS-009 | Longford | North | P&C rebuild with new control building (7 bays) | Jun 2034
PRP-087 | TS-055 | High Falls | North | Feeder relay replacement, 8 bays, with panel rewiring | Jul 2034
PRP-088 | DS-056 | Crowton | South | P&C rebuild with new control building (8 bays) | Aug 2034
PRP-089 | DS-060 | Otterville | South | Feeder relay replacement, 2 bays, with panel rewiring | Sep 2034
PRP-090 | DS-057 | Fern River | Central | Replace feeder protection, 5 bays | Oct 2034
PRP-091 | DS-003 | Grey Mills | South | Protection and control panel replacement (4 feeder bays) | Nov 2034
PRP-092 | DS-015 | Birch Bay | South | Feeder relay replacement, 8 bays, with panel rewiring | Dec 2034
PRP-093 | DS-089 | Greyford | South | Protection and control panel replacement (8 feeder bays) | Jan 2035
PRP-094 | DS-121 | Otterdale | Central | Replace VPR-340 feeder relays (3) and RTU | Feb 2035
PRP-095 | DS-031 | Oak Falls | Central | Replace VPR-340 feeder relays (3) and RTU | Mar 2035
PRP-096 | DS-129 | Lake Mills | North | Replace feeder protection, 1 bays | Apr 2035
PRP-097 | DS-013 | Springbrook | Central | Replace feeder protection, 2 bays | May 2035
PRP-098 | DS-076 | Iron Junction | South | P&C rebuild with new control building (5 bays) | Jun 2035
PRP-099 | DS-065 | Sugar River | Central | Protection and control panel replacement (6 feeder bays) | Jul 2035
PRP-100 | DS-079 | Portford | North | Replace VPR-340 feeder relays (7) and RTU | Aug 2035
PRP-101 | DS-132 | Oakdale | North | Feeder relay replacement, 5 bays, with panel rewiring | Sep 2035
PRP-102 | TS-088 | Otterton | Central | Replace VPR-340 feeder relays (8) and RTU | Oct 2035
PRP-103 | DS-092 | Fern Mills | North | Protection and control panel replacement (5 feeder bays) | Nov 2035
| DS-023 | Grey Bridge | Central | Protection and control panel replacement (8 feeder bays) | Not in programme period
| DS-040 | Northbrook | North | Replace feeder protection, 8 bays | Not in programme period
| DS-073 | Mapledale | Central | Replace feeder protection, 9 bays | Not in programme period
| DS-086 | Greywood | Central | Feeder relay replacement, 6 bays, with panel rewiring | Not in programme period
| DS-091 | Port Mills | South | Replace feeder protection, 6 bays | Not in programme period
| DS-093 | Rock Landing | North | Replace feeder protection, 3 bays | Not in programme period
| DS-123 | Bearton | South | Replace VPR-340 feeder relays (8) and RTU | Not in programme period
| DS-141 | Crow Mills | South | Replace VPR-340 feeder relays (2) and RTU | Not in programme period
| TS-085 | Mosshurst | North | P&C rebuild with new control building (1 bays) | Not in programme period

## 2025 plan (superseded)
Protection Renewal Programme, 2025 planning version (superseded by the approved 2026 programme)
Scheme | Substation code | Substation | Region | Scope | Commissioning month
PRP-001 | DS-046 | Hawkford | North | Replace VPR-340 feeder relays (3) and RTU | Jan 2027
PRP-002 | DS-054 | Long River | North | Protection and control panel replacement (4 feeder bays) | Jan 2027
PRP-003 | DS-120 | Lakewood | South | Feeder protection upgrade, 3 bays, IEC 61850 station bus | Jan 2027
PRP-004 | DS-127 | Kingsmount | Central | Replace feeder protection, 4 bays | Feb 2027
PRP-005 | DS-080 | Spring Ridge | South | Replace VPR-340 feeder relays (6) and RTU | Mar 2027
PRP-006 | TS-025 | Brant Falls | North | Protection and control panel replacement (6 feeder bays) | Apr 2027
PRP-007 | TS-058 | Elm Point | North | P&C rebuild with new control building (1 bays) | May 2027
PRP-008 | DS-119 | Cedar Junction | North | P&C rebuild with new control building (1 bays) | Jun 2027
PRP-009 | DS-014 | Cedarbrook | Central | Protection and control panel replacement (2 feeder bays) | Jul 2027
PRP-010 | DS-028 | Silver Ridge | North | Replace feeder protection, 2 bays | Aug 2027
PRP-011 | DS-033 | Elmdale | North | Replace VPR-340 feeder relays (4) and RTU | Sep 2027
PRP-012 | DS-134 | Mossfield | North | Replace feeder protection, 2 bays | Sep 2027
PRP-013 | DS-016 | Long Road | South | Feeder protection upgrade, 2 bays, IEC 61850 station bus | Jan 2028
PRP-014 | DS-002 | West River | North | Replace VPR-340 feeder relays (5) and RTU | Feb 2028
PRP-015 | DS-064 | Kettle Bridge | North | Replace VPR-340 feeder relays (5) and RTU | Mar 2028
PRP-016 | DS-139 | Birch Landing | South | Feeder protection upgrade, 8 bays, IEC 61850 station bus | Mar 2028
PRP-017 | DS-038 | Whitemount | North | Feeder protection upgrade, 4 bays, IEC 61850 station bus | Apr 2028
PRP-018 | TS-110 | Red Creek | Central | Replace VPR-340 feeder relays (7) and RTU | Apr 2028
PRP-019 | DS-106 | Willow Bridge | Central | Protection and control panel replacement (9 feeder bays) | May 2028
PRP-020 | DS-069 | Sand Landing | Central | Protection and control panel replacement (6 feeder bays) | Jun 2028
PRP-021 | DS-122 | Ash Bridge | South | Feeder protection upgrade, 8 bays, IEC 61850 station bus | Jul 2028
PRP-022 | DS-075 | Ash Creek | North | Replace VPR-340 feeder relays (1) and RTU | Sep 2028
PRP-023 | DS-104 | Stone Mills | South | Feeder protection upgrade, 6 bays, IEC 61850 station bus | Nov 2028
PRP-024 | TS-138 | Kingston | Central | Replace feeder protection, 8 bays | Dec 2028
PRP-025 | DS-001 | Cedar Road | Central | Feeder protection upgrade, 4 bays, IEC 61850 station bus | Feb 2029
PRP-026 | DS-115 | Crow Junction | Central | Feeder protection upgrade, 3 bays, IEC 61850 station bus | Feb 2029
PRP-027 | DS-045 | Rock Hill | South | Feeder protection upgrade, 4 bays, IEC 61850 station bus | Mar 2029
PRP-028 | DS-108 | Whitefield | South | Protection and control panel replacement (2 feeder bays) | Apr 2029
PRP-029 | DS-035 | Clearton | South | Feeder relay replacement, 7 bays, with panel rewiring | May 2029
PRP-030 | DS-029 | Bear River | Central | Feeder protection upgrade, 4 bays, IEC 61850 station bus | Jun 2029
PRP-031 | DS-022 | Wolfford | North | Replace feeder protection, 6 bays | Jul 2029
PRP-032 | DS-061 | Spring River | Central | Feeder protection upgrade, 4 bays, IEC 61850 station bus | Jul 2029
PRP-033 | TS-090 | Fox Mills | North | Protection and control panel replacement (7 feeder bays) | Aug 2029
PRP-034 | DS-019 | Glen Bay | North | Replace feeder protection, 4 bays | Sep 2029
PRP-035 | DS-107 | Long Ridge | North | Feeder relay replacement, 7 bays, with panel rewiring | Sep 2029
PRP-036 | DS-068 | Iron Corners | South | Feeder relay replacement, 3 bays, with panel rewiring | Oct 2029
PRP-037 | DS-036 | Whitedale | Central | P&C rebuild with new control building (8 bays) | Nov 2029
PRP-038 | DS-128 | Rock Bay | Central | Feeder protection upgrade, 4 bays, IEC 61850 station bus | Nov 2029
PRP-039 | DS-137 | Bear Landing | South | Protection and control panel replacement (5 feeder bays) | Nov 2029
PRP-040 | TS-039 | Deerwood | North | Replace feeder protection, 1 bays | Jan 2030
PRP-041 | DS-062 | Oakton | North | Replace VPR-340 feeder relays (7) and RTU | Feb 2030
PRP-042 | DS-131 | Springwood | Central | Feeder protection upgrade, 5 bays, IEC 61850 station bus | Feb 2030
PRP-043 | DS-126 | Long Falls | South | P&C rebuild with new control building (7 bays) | Apr 2030
PRP-044 | DS-084 | Mill Landing | Central | Replace feeder protection, 3 bays | Jun 2030
PRP-045 | DS-135 | Fern Point | North | Protection and control panel replacement (5 feeder bays) | Jun 2030
PRP-046 | DS-067 | Hawk Hill | South | Protection and control panel replacement (6 feeder bays) | Jul 2030
PRP-047 | DS-020 | Heronwood | North | Feeder relay replacement, 7 bays, with panel rewiring | Sep 2030
PRP-048 | DS-011 | Port Landing | South | Replace feeder protection, 7 bays | Oct 2030
PRP-049 | DS-021 | Rock Point | North | Feeder protection upgrade, 1 bays, IEC 61850 station bus | Nov 2030
PRP-050 | DS-026 | Hawk Junction | Central | Replace VPR-340 feeder relays (7) and RTU | Jan 2031
PRP-051 | DS-140 | Elmfield | South | Feeder protection upgrade, 6 bays, IEC 61850 station bus | Feb 2031
PRP-052 | DS-114 | Glenhurst | Central | Replace VPR-340 feeder relays (9) and RTU | Mar 2031
PRP-053 | DS-050 | Maplebrook | North | Protection and control panel replacement (4 feeder bays) | May 2031
PRP-054 | DS-010 | Hawk Bay | Central | Protection and control panel replacement (5 feeder bays) | Jul 2031
PRP-055 | DS-032 | Spring Corners | North | Protection and control panel replacement (8 feeder bays) | Oct 2031
PRP-056 | DS-116 | Rockmount | South | Replace VPR-340 feeder relays (6) and RTU | Oct 2031
PRP-057 | DS-117 | Willowhurst | Central | Feeder protection upgrade, 9 bays, IEC 61850 station bus | Dec 2031
PRP-058 | DS-112 | Sandfield | North | Feeder relay replacement, 2 bays, with panel rewiring | Jan 2032
PRP-059 | DS-047 | Cedar Ridge | South | Protection and control panel replacement (7 feeder bays) | Feb 2032
PRP-060 | DS-070 | Moss Creek | South | P&C rebuild with new control building (6 bays) | Mar 2032
PRP-061 | DS-095 | Ashhurst | South | Feeder relay replacement, 6 bays, with panel rewiring | Apr 2032
PRP-062 | DS-109 | Fernwood | Central | Replace feeder protection, 5 bays | Jul 2032
PRP-063 | DS-124 | Cedar Mills | North | Protection and control panel replacement (8 feeder bays) | Jul 2032
PRP-064 | TS-055 | High Falls | North | Feeder relay replacement, 8 bays, with panel rewiring | Aug 2032
PRP-065 | DS-007 | Stone Bridge | South | P&C rebuild with new control building (4 bays) | Sep 2032
PRP-066 | DS-087 | Wolf River | North | Feeder protection upgrade, 3 bays, IEC 61850 station bus | Sep 2032
PRP-067 | DS-111 | Cedar Bridge | Central | Feeder protection upgrade, 8 bays, IEC 61850 station bus | Oct 2032
PRP-068 | DS-125 | Glenfield | South | Replace VPR-340 feeder relays (7) and RTU | Nov 2032
PRP-069 | DS-043 | Moss Road | North | P&C rebuild with new control building (2 bays) | Dec 2032
PRP-070 | DS-082 | Wolf Landing | Central | Replace feeder protection, 7 bays | Dec 2032
PRP-071 | DS-071 | Sugarford | South | Feeder relay replacement, 3 bays, with panel rewiring | Jan 2033
PRP-072 | DS-041 | Brant Ridge | North | P&C rebuild with new control building (7 bays) | Feb 2033
PRP-073 | DS-053 | Hawk Mills | North | Replace feeder protection, 3 bays | Feb 2033
PRP-074 | DS-096 | Iron Point | South | Feeder protection upgrade, 5 bays, IEC 61850 station bus | Mar 2033
PRP-075 | DS-094 | Willowwood | North | Protection and control panel replacement (3 feeder bays) | Apr 2033
PRP-076 | TS-081 | Rockwood | North | P&C rebuild with new control building (4 bays) | Apr 2033
PRP-077 | DS-004 | Otter Landing | South | Replace VPR-340 feeder relays (3) and RTU | May 2033
PRP-078 | DS-101 | Silverford | Central | Feeder relay replacement, 4 bays, with panel rewiring | Jun 2033
PRP-079 | TS-100 | Silver Falls | North | Feeder protection upgrade, 4 bays, IEC 61850 station bus | Aug 2033
PRP-080 | DS-063 | Heron Falls | South | Protection and control panel replacement (1 feeder bays) | Sep 2033
PRP-081 | DS-030 | Millbrook | North | P&C rebuild with new control building (5 bays) | Oct 2033
PRP-082 | DS-027 | North Hill | Central | Protection and control panel replacement (9 feeder bays) | Nov 2033
PRP-083 | DS-005 | Silver River | Central | Feeder protection upgrade, 8 bays, IEC 61850 station bus | Dec 2033
PRP-084 | DS-059 | Clear Point | North | Feeder relay replacement, 2 bays, with panel rewiring | Jan 2034
PRP-085 | TS-098 | Redwood | North | Protection and control panel replacement (6 feeder bays) | Feb 2034
PRP-086 | DS-018 | Sandville | North | Feeder protection upgrade, 2 bays, IEC 61850 station bus | May 2034
PRP-087 | DS-009 | Longford | North | P&C rebuild with new control building (7 bays) | Jun 2034
PRP-088 | DS-056 | Crowton | South | P&C rebuild with new control building (8 bays) | Aug 2034
PRP-089 | DS-060 | Otterville | South | Feeder relay replacement, 2 bays, with panel rewiring | Sep 2034
PRP-090 | DS-057 | Fern River | Central | Replace feeder protection, 5 bays | Oct 2034
PRP-091 | DS-003 | Grey Mills | South | Protection and control panel replacement (4 feeder bays) | Nov 2034
PRP-092 | DS-089 | Greyford | South | Protection and control panel replacement (8 feeder bays) | Jan 2035
PRP-093 | DS-121 | Otterdale | Central | Replace VPR-340 feeder relays (3) and RTU | Feb 2035
PRP-094 | DS-031 | Oak Falls | Central | Replace VPR-340 feeder relays (3) and RTU | Mar 2035
PRP-095 | DS-129 | Lake Mills | North | Replace feeder protection, 1 bays | Apr 2035
PRP-096 | DS-013 | Springbrook | Central | Replace feeder protection, 2 bays | May 2035
PRP-097 | DS-076 | Iron Junction | South | P&C rebuild with new control building (5 bays) | Jun 2035
PRP-098 | DS-065 | Sugar River | Central | Protection and control panel replacement (6 feeder bays) | Jul 2035
PRP-099 | DS-079 | Portford | North | Replace VPR-340 feeder relays (7) and RTU | Aug 2035
PRP-100 | DS-132 | Oakdale | North | Feeder relay replacement, 5 bays, with panel rewiring | Sep 2035
PRP-101 | TS-088 | Otterton | Central | Replace VPR-340 feeder relays (8) and RTU | Oct 2035
PRP-102 | DS-092 | Fern Mills | North | Protection and control panel replacement (5 feeder bays) | Nov 2035
PRP-103 | DS-015 | Birch Bay | South | Feeder relay replacement, 8 bays, with panel rewiring | Apr 2037
| DS-023 | Grey Bridge | Central | Protection and control panel replacement (8 feeder bays) | Not in programme period
| DS-040 | Northbrook | North | Replace feeder protection, 8 bays | Not in programme period
| DS-073 | Mapledale | Central | Replace feeder protection, 9 bays | Not in programme period
| DS-086 | Greywood | Central | Feeder relay replacement, 6 bays, with panel rewiring | Not in programme period
| DS-091 | Port Mills | South | Replace feeder protection, 6 bays | Not in programme period
| DS-093 | Rock Landing | North | Replace feeder protection, 3 bays | Not in programme period
| DS-123 | Bearton | South | Replace VPR-340 feeder relays (8) and RTU | Not in programme period
| DS-141 | Crow Mills | South | Replace VPR-340 feeder relays (2) and RTU | Not in programme period
| TS-085 | Mosshurst | North | P&C rebuild with new control building (1 bays) | Not in programme period

## Notes
Commissioning month is the month the new protection panel is placed in service; the VPR-340 relays at that substation are removed from service in the same month.
Substations rebuilt under the 2022-2025 station renewals no longer carry VPR-340 relays and are not listed.
Substations marked 'Not in programme period' keep their VPR-340 relays beyond December 2035.
The 2026 programme defers 16 schemes and brings 7 forward against the 2025 planning version.