## Zone schedule
Every zone finished by 2037 at $27.1 million a year: lead service line replacement schedule, 2027 to 2037
Hollins Ford Regional Water District, LSLR programme office. Plan revision 2 zones in priority order; plan cost in 2027 dollars at the 2027 unit cost schedule. Prepared 11 January 2027 for the board meeting of 19 January 2027.
Priority | Zone | Zone name | Lead and GRR lines to replace | Plan cost ($) | Cumulative plan cost ($ million) | Cumulative programme years | Finish year
1 | RZ-07 | Orchard Ridge | 1670 | 23100000 | 23.1 | 0.85 | 2027
2 | RZ-02 | Canal Street | 2140 | 34800000 | 57.9 | 2.14 | 2029
3 | RZ-11 | Southgate | 1960 | 29800000 | 87.7 | 3.24 | 2030
4 | RZ-04 | North Linden | 1480 | 24400000 | 112.1 | 4.14 | 2031
5 | RZ-09 | Burkhart | 1830 | 28100000 | 140.2 | 5.17 | 2032
6 | RZ-01 | Foundry Hill | 1970 | 28600000 | 168.9 | 6.23 | 2033
7 | RZ-05 | Depot Square | 1750 | 26800000 | 195.7 | 7.22 | 2034
8 | RZ-12 | Kittering Village | 930 | 15200000 | 210.9 | 7.78 | 2034
9 | RZ-03 | Millrace | 1290 | 20300000 | 231.1 | 8.53 | 2035
10 | RZ-08 | Elm Park | 1380 | 22100000 | 253.3 | 9.35 | 2036
11 | RZ-10 | Lakeview Terrace | 770 | 13000000 | 266.2 | 9.82 | 2036
12 | RZ-06 | Wexley | 1080 | 18400000 | 284.7 | 10.5 | 2037
|  | All twelve zones |  |  | 284.7 | 10.5
Last zone: RZ-06 Wexley, finished in programme year 2037, inside the 1 November 2037 deadline.
Lines to replace: the zone's Lead and GRR lines plus its Lead Status Unknown lines at the share found lead or GRR in their construction era on the segments verified whole (sheet Unknown-line shares).
A zone is finished in the programme year in which the running total of the appropriation covers the running total of plan cost through it (plan 5.3). Lines rounded to the nearest ten and costs to the nearest $100,000; cumulative columns from unrounded zone costs.

## Unknown-line shares
Share of lines with no usable tap card expected to prove lead or GRR, by construction era
Lines with no usable tap card on the 78 main segments where every service line has been verified (each segment's lines exposed and verified together when its main was replaced, 2023 to 2026).
Construction era | Lines verified | Found lead or GRR | Share | Share across every verification (for comparison)
Built before 1930 | 792 | 440 | 0.556 | 0.763
Built 1930 to 1949 | 304 | 96 | 0.316 | 0.585
Built 1950 to 1988 | 168 | 14 | 0.083 | 0.217
Every other verification on file was a visit to one line because something pointed at it (a customer report, a sampling site, a leak on the service, the 2024 ranking), so its shares run high: priced at them the last zone would finish in 2039.

## 2026 contract payments
Paid per full replacement completed, 2026 replacement contracts
Bid price, extra service length and restoration on each site's latest closing, plus each approved change order once, over the full replacements completed in the quarter (Eastern time). Dollars.
Contract | Contractor | Q1 2026 | Q2 2026 | Q3 2026 | Q4 2026
2026-LSL-01 | Brannigan Excavating Inc | 13890 | 13494 | 13416 | 13673
2026-LSL-02 | Tri-County Underground | 14509 | 13937 | 13903 | 13568
2026-LSL-03 | Kestrel Pipe and Utility | 14488 | 14459 | 15008 | 14784
Full replacements completed
2026-LSL-01 | Brannigan Excavating Inc | 71 | 90 | 162 | 61
2026-LSL-02 | Tri-County Underground | 41 | 85 | 132 | 53
2026-LSL-03 | Kestrel Pipe and Utility | 23 | 20 | 21 | 13
Tri-County Underground was paid under vendor V-20877 to 12 July 2026 and V-31560 from 13 July 2026; both are contract 2026-LSL-02.

## Access agreements
Service lines with a signed access agreement, by zone, 8 January 2027
Distinct service lines with a right-of-entry agreement signed and not withdrawn, counted in the zone the inventory gives the line today.
Priority | Zone | Zone name | Service lines with a signed agreement
1 | RZ-07 | Orchard Ridge | 975
2 | RZ-02 | Canal Street | 1217
3 | RZ-11 | Southgate | 1118
4 | RZ-04 | North Linden | 954
5 | RZ-09 | Burkhart | 1017
6 | RZ-01 | Foundry Hill | 857
7 | RZ-05 | Depot Square | 889
8 | RZ-12 | Kittering Village | 518
9 | RZ-03 | Millrace | 626
10 | RZ-08 | Elm Park | 663
11 | RZ-10 | Lakeview Terrace | 368
12 | RZ-06 | Wexley | 539