## Approved 2026
Protection Renewal Program 2026-2035, approved by the Board 19 March 2026 (resolution 2026-07)
Scheme | Stage | Substation code | Substation | Region | Bays | Scope | Commissioning month
PRP-041 |  | DS-014 | Bexhurst | South | F01-F04 | Replace feeder protection F01-F04, panel rewiring and DC upgrade | 2027-01-01
PRP-068 |  | DS-022 | Rose Lake | North | F01-F10 | Feeder protection and control replacement F01-F10 | 2027-01-01
PRP-133 |  | DS-117 | Mosswell | South | F01-F08 | P&C rebuild with new control building, feeders F01-F08 | 2027-02-01
PRP-150 |  | DS-087 | Kelville | Central | F01-F09 | Feeder protection replacement F01-F09, new P&C panels | 2027-02-01
PRP-017 |  | DS-063 | Ockham | Central | F01-F08 | Feeder protection replacement F01-F08, new P&C panels | 2027-03-01
PRP-147 | 1 | DS-060 | Upmere | South | F01-F05 | Stage 1: replace feeder relays F01-F05, station bus | 2027-04-01
PRP-183 | 1 | DS-016 | Mormere | South | F01-F06 | Stage 1: P&C panels F01-F06 | 2027-04-01
PRP-035 |  | DS-095 | Eldercliff | Central | F01, F04-F05, F07-F12, RTU | Replace VPR-220 relays F01, F04-F05, F07-F12 and RTU, new DC system | 2027-07-01
PRP-105 |  | DS-003 | Dalside | North | F02-F04, F06, F08, F10 | Replace VPR-220 feeder protection F02-F04, F06, F08, F10 | 2027-09-01
PRP-024 |  | DS-007 | Tamhurst | North | F01-F08 | Feeder protection replacement F01-F08, new P&C panels | 2027-10-01
PRP-182 |  | DS-103 | Gildale | North | F01-F09 | Feeder protection replacement F01-F09, new P&C panels, spare bay F09 fitted out | 2027-10-01
PRP-280 | 1 | TS-11 | Yarbury | North | F01-F13 | Stage 1: replace feeder relays F01-F13, station bus | 2027-10-01
PRP-243 | 1 | DS-082 | Stagbury | North | F01-F06 | Stage 1: P&C panels F01-F06 | 2027-11-01
PRP-258 | 1 | DS-091 | Saltley | Central | F01-F06 | Stage 1: feeder protection F01-F06, new control building | 2027-12-01
PRP-129 |  | DS-042 | Redbury | Central | F01-F09 | Replace feeder relays F01-F09 and RTU, IEC 61850 station bus | 2028-04-01
PRP-206 |  | TS-02 | Blackhaven | North | F01-F04, F06, F08-F12 | VPR-220 feeder relay replacement F01-F04, F06, F08-F12, panel rewiring | 2028-04-01
PRP-272 |  | DS-120 | Belhurst | North | F01-F05 | P&C rebuild with new control building, feeders F01-F05 | 2028-04-01
PRP-176 |  | DS-045 | Fish Creek | North | F01-F09 | Replace feeder protection F01-F09, panel rewiring and DC upgrade | 2028-05-01
PRP-276 | 1 | DS-100 | Atherhurst | South | F01-F06 | Stage 1: P&C panels F01-F06 | 2028-05-01
PRP-025 | 1 | DS-009 | Kingview | Central | F01-F05 | Stage 1: feeder protection F01-F05, new control building | 2028-06-01
PRP-049 |  | DS-074 | Clayhaven | Central | F01-F11 | Replace feeder relays F01-F11 and RTU, IEC 61850 station bus, spare bay F11 fitted out | 2028-06-01
PRP-185 |  | TS-14 | Terhaven | North | F03, F07, F09-F13, F16-F19 | Replace VPR-220 feeder protection F03, F07, F09-F13, F16-F19 | 2028-06-01
PRP-167 | 1 | DS-106 | Swanwood | South | F01-F05 | Stage 1: replace feeder relays F01-F05, station bus | 2028-07-01
PRP-156 |  | DS-027 | Burside | South | F01-F09 | Replace feeder relays F01-F09 and RTU, IEC 61850 station bus | 2028-10-01
PRP-236 | 1 | DS-110 | Ash Point | Central | F01-F07 | Stage 1: feeder protection F01-F07, new control building | 2028-10-01
PRP-260 |  | DS-005 | Branville | Central | F01-F07 | Replace feeder protection F01-F07, panel rewiring and DC upgrade | 2028-10-01
PRP-095 | 1 | DS-037 | Gold Creek | North | F01-F07 | Stage 1: P&C panels F01-F07 | 2028-11-01
PRP-114 |  | DS-011 | Long Falls | South | F01-F07 | Feeder protection and control replacement F01-F07 | 2028-11-01
PRP-104 |  | DS-054 | Silver Mills | Central | F01-F07 | P&C rebuild with new control building, feeders F01-F07 | 2029-02-01
PRP-117 |  | DS-064 | Whitmere | Central | F01-F10 | Replace feeder relays F01-F10 and RTU, IEC 61850 station bus | 2029-04-01
PRP-141 | 1 | DS-119 | Greencroft | North | F01-F04 | Stage 1: feeder protection F01-F04, new control building | 2029-04-01
PRP-200 |  | DS-067 | Richgate | South | F01-F09 | Replace feeder relays F01-F09 and RTU, IEC 61850 station bus | 2029-04-01
PRP-126 |  | DS-071 | Reedby | North | F01-F07 | Replace feeder relays F01-F07 and RTU, IEC 61850 station bus | 2029-05-01
PRP-207 |  | DS-020 | Clearbury | North | F01, F03, F05 | Replace VPR-220 relays F01, F03, F05, new DC system | 2029-05-01
PRP-213 | 1 | DS-092 | Alder Mills | North | F01-F05 | Stage 1: P&C panels F01-F05 | 2029-05-01
PRP-183 | 2 | DS-016 | Mormere | South | F07-F11 | Stage 2: P&C panels F07-F11, decommission old building | 2029-06-01
PRP-280 | 2 | TS-11 | Yarbury | North | F14-F24 | Stage 2: replace feeder relays F14-F24 | 2029-06-01
PRP-089 |  | DS-125 | Lark Mills | Central | F01-F09 | Replace feeder protection F01-F09, panel rewiring and DC upgrade | 2029-09-01
PRP-107 |  | DS-039 | Owlbury | Central | F01-F10 | P&C rebuild with new control building, feeders F01-F10 | 2029-11-01
PRP-139 |  | DS-028 | Seldale | North | F01-F09 | P&C rebuild with new control building, feeders F01-F09 | 2029-11-01
PRP-242 | 1 | DS-072 | Lindale | Central | F01-F04 | Stage 1: P&C panels F01-F04 | 2029-11-01
PRP-248 | 1 | DS-089 | Beechwood | South | F01-F05 | Stage 1: P&C panels F01-F05 | 2030-03-01
PRP-268 |  | TS-12 | Wrenmere | North | F02-F05, F07-F08, F15, F18, RTU | Replace VPR-220 feeder protection F02-F05, F07-F08, F15, F18 and RTU | 2030-03-01
PRP-097 |  | DS-053 | Greyside | South | F01-F10 | Feeder protection replacement F01-F10, new P&C panels | 2030-04-01
PRP-123 |  | DS-115 | Coldmount | South | F01-F10 | Feeder protection replacement F01-F10, new P&C panels | 2030-04-01
PRP-243 | 2 | DS-082 | Stagbury | North | F07-F11 | Stage 2: P&C panels F07-F11, decommission old building | 2030-04-01
PRP-252 | 1 | DS-080 | Slatemere | Central | F01-F04 | Stage 1: replace feeder relays F01-F04, station bus | 2030-04-01
PRP-258 | 2 | DS-091 | Saltley | Central | F07-F14 | Stage 2: feeder protection F07-F14, RTU cutover | 2030-04-01
PRP-162 |  | DS-083 | Wolfbrook | North | F01-F05 | Replace feeder relays F01-F05 and RTU, IEC 61850 station bus | 2030-05-01
PRP-169 |  | DS-121 | Midwood | South | F01-F08 | P&C rebuild with new control building, feeders F01-F08 | 2030-05-01
PRP-276 | 2 | DS-100 | Atherhurst | South | F07-F13 | Stage 2: P&C panels F07-F13, decommission old building | 2030-05-01
PRP-044 |  | DS-099 | Deer Lake | Central | F02, F04-F05, F10, RTU | Replace VPR-220 relays F02, F04-F05, F10 and RTU, new DC system | 2030-06-01
PRP-088 |  | DS-057 | Amber Mills | South | F01-F09 | Replace feeder relays F01-F09 and RTU, IEC 61850 station bus | 2030-07-01
PRP-147 | 2 | DS-060 | Upmere | South | F06-F11 | Stage 2: replace feeder relays F06-F11 | 2030-09-01
PRP-167 | 2 | DS-106 | Swanwood | South | F06-F13 | Stage 2: replace feeder relays F06-F13 | 2030-09-01
PRP-201 |  | DS-069 | Arrowmount | North | F01-F05 | Feeder protection replacement F01-F05, new P&C panels | 2030-10-01
PRP-102 | 1 | TS-17 | Bellfield | South | F01-F16 | Stage 1: P&C panels F01-F16 | 2030-12-01
PRP-245 |  | DS-101 | Wargate | Central | F01-F07 | Feeder protection replacement F01-F07, new P&C panels | 2031-01-01
PRP-081 |  | DS-090 | Radby | Central | F01-F07 | Feeder protection and control replacement F01-F07 | 2031-02-01
PRP-227 |  | DS-017 | Wilbrook | Central | F01-F07 | Feeder protection replacement F01-F07, new P&C panels | 2031-03-01
PRP-034 |  | DS-044 | Otterworth | South | F01-F09 | Feeder protection and control replacement F01-F09 | 2031-04-01
PRP-095 | 2 | DS-037 | Gold Creek | North | F08-F12 | Stage 2: P&C panels F08-F12, decommission old building | 2031-04-01
PRP-099 |  | DS-024 | Fern Falls | North | F01-F10 | Replace feeder protection F01-F10, panel rewiring and DC upgrade | 2031-04-01
PRP-171 |  | TS-07 | Rockhurst | North | F01-F03, F05-F07, F09-F12 | Replace VPR-220 feeder protection F01-F03, F05-F07, F09-F12 | 2031-04-01
PRP-173 |  | DS-055 | Wendmore | South | F01-F04, F06-F07, RTU | VPR-220 feeder relay replacement F01-F04, F06-F07 and RTU, panel rewiring | 2031-05-01
PRP-218 | 1 | DS-025 | Bradmount | South | F01-F05 | Stage 1: feeder protection F01-F05, new control building | 2031-05-01
PRP-141 | 2 | DS-119 | Greencroft | North | F05-F11 | Stage 2: feeder protection F05-F11, RTU cutover | 2031-06-01
PRP-213 | 2 | DS-092 | Alder Mills | North | F06-F12 | Stage 2: P&C panels F06-F12, decommission old building | 2031-06-01
PRP-215 |  | DS-043 | Flintdale | North | F01, F07 | VPR-220 feeder relay replacement F01, F07, panel rewiring | 2031-06-01
PRP-193 |  | DS-051 | Pine Mills | North | F05 | Replace VPR-220 feeder protection F05 | 2031-07-01
PRP-255 |  | DS-065 | Hollydale | North | F01-F07 | Feeder protection replacement F01-F07, new P&C panels | 2031-07-01
PRP-094 |  | DS-094 | Lynville | South | F01-F08 | Replace feeder relays F01-F08 and RTU, IEC 61850 station bus | 2031-08-01
PRP-262 | 1 | DS-107 | Laurel Hill | Central | F01-F06 | Stage 1: replace feeder relays F01-F06, station bus | 2031-08-01
PRP-190 |  | DS-046 | Heathview | Central | F01-F10 | Replace feeder relays F01-F10 and RTU, IEC 61850 station bus | 2031-09-01
PRP-046 |  | DS-019 | Winstead | Central | F01-F07 | Feeder protection replacement F01-F07, new P&C panels | 2031-10-01
PRP-152 | 1 | TS-10 | Ravenport | South | F01-F07 | Stage 1: P&C panels F01-F07 | 2031-10-01
PRP-210 |  | DS-085 | Weldale | Central | F01-F05 | P&C rebuild with new control building, feeders F01-F05 | 2031-10-01
PRP-220 | 1 | DS-059 | Birchworth | North | F01-F05 | Stage 1: P&C panels F01-F05 | 2031-10-01
PRP-063 |  | DS-084 | Sand Junction | Central | F01-F08 | Feeder protection and control replacement F01-F08 | 2031-11-01
PRP-242 | 2 | DS-072 | Lindale | Central | F05-F11 | Stage 2: P&C panels F05-F11, decommission old building | 2031-11-01
PRP-011 |  | DS-035 | Corn River | North | F01, F03-F05, F07-F08, RTU | VPR-220 feeder relay replacement F01, F03-F05, F07-F08 and RTU, panel rewiring | 2032-04-01
PRP-083 |  | DS-066 | Harton | Central | F01-F08 | Replace feeder relays F01-F08 and RTU, IEC 61850 station bus | 2032-04-01
PRP-239 | 1 | DS-050 | Sherford | Central | F01-F07 | Stage 1: feeder protection F01-F07, new control building | 2032-04-01
PRP-249 |  | TS-16 | Ipsgate | Central | F01, F03-F09, F12 | Replace VPR-220 feeder protection F01, F03-F09, F12 | 2032-04-01
PRP-252 | 2 | DS-080 | Slatemere | Central | F05-F11 | Stage 2: replace feeder relays F05-F11 | 2032-04-01
PRP-037 |  | DS-004 | Highview | North | F01-F09 | Replace feeder protection F01-F09, panel rewiring and DC upgrade | 2032-05-01
PRP-203 | 1 | TS-15 | Quarryhaven | South | F01-F08 | Stage 1: P&C panels F01-F08 | 2032-05-01
PRP-025 | 2 | DS-009 | Kingview | Central | F06-F11 | Stage 2: feeder protection F06-F11, RTU cutover | 2032-06-01
PRP-165 |  | DS-108 | Kilwood | South | F01-F09 | P&C rebuild with new control building, feeders F01-F09, spare bay F09 fitted out | 2032-06-01
PRP-222 |  | DS-029 | Loxside | South | F01-F10 | Feeder protection replacement F01-F10, new P&C panels | 2032-06-01
PRP-236 | 2 | DS-110 | Ash Point | Central | F08-F15 | Stage 2: feeder protection F08-F15, RTU cutover | 2032-06-01
PRP-163 |  | DS-068 | Fairwell | North | F01-F10 | P&C rebuild with new control building, feeders F01-F10 | 2032-10-01
PRP-232 | 1 | DS-015 | Mapleham | South | F01-F04 | Stage 1: feeder protection F01-F04, new control building | 2032-10-01
PRP-014 |  | DS-096 | Camden Hill | North | F01-F10 | Replace feeder relays F01-F10 and RTU, IEC 61850 station bus | 2032-11-01
PRP-132 |  | DS-010 | Elmwell | North | F01-F02 | Replace VPR-220 feeder protection F01-F02 | 2032-11-01
PRP-159 | 1 | DS-078 | Stamwell | South | F01-F09 | Stage 1: replace feeder relays F01-F09, station bus | 2032-11-01
PRP-270 |  | DS-062 | Aspenside | South | F02-F05 | Replace VPR-220 feeder protection F02-F05 | 2032-11-01
PRP-047 | 1 | TS-08 | Cran Junction | North | F01-F12 | Stage 1: P&C panels F01-F12 | 2033-03-01
PRP-071 |  | TS-03 | Ranburn | Central | F01-F15 | Replace feeder protection F01-F15, panel rewiring and DC upgrade | 2033-03-01
PRP-109 |  | DS-038 | Stoneham | Central | F01-F11 | Feeder protection and control replacement F01-F11 | 2033-03-01
PRP-278 |  | DS-102 | Calton | Central | F01-F10 | Feeder protection replacement F01-F10, new P&C panels | 2033-03-01
PRP-057 |  | DS-076 | Penville | South | F01-F05 | Feeder protection and control replacement F01-F05 | 2033-04-01
PRP-059 |  | DS-049 | Malbrook | North | F01-F13 | P&C rebuild with new control building, feeders F01-F13 | 2033-04-01
PRP-136 | 1 | TS-05 | Kirkcliff | Central | F01-F11 | Stage 1: replace feeder relays F01-F11, station bus | 2033-04-01
PRP-218 | 2 | DS-025 | Bradmount | South | F06-F11 | Stage 2: feeder protection F06-F11, RTU cutover | 2033-04-01
PRP-051 | 1 | TS-01 | Barrow Junction | North | F01-F08 | Stage 1: replace feeder relays F01-F08, station bus | 2033-05-01
PRP-179 |  | DS-006 | Crowmere | Central | F01-F10 | P&C rebuild with new control building, feeders F01-F10 | 2033-06-01
PRP-263 |  | DS-114 | Kettleview | South | F01-F08 | Feeder protection replacement F01-F08, new P&C panels | 2033-06-01
PRP-224 |  | DS-086 | Balbrook | North | F01-F12 | Feeder protection and control replacement F01-F12 | 2033-08-01
PRP-102 | 2 | TS-17 | Bellfield | South | F17-F34 | Stage 2: P&C panels F17-F34, decommission old building | 2033-09-01
PRP-237 |  | DS-056 | Sableburn | Central | F01-F07 | Feeder protection and control replacement F01-F07 | 2033-09-01
PRP-248 | 2 | DS-089 | Beechwood | South | F06-F11 | Stage 2: P&C panels F06-F11, decommission old building | 2033-10-01
PRP-039 |  | DS-048 | Oxby | South | F01-F10 | P&C rebuild with new control building, feeders F01-F10 | 2033-11-01
PRP-234 |  | DS-075 | Edgecliff | North | F01-F09 | Feeder protection replacement F01-F09, new P&C panels | 2033-11-01
PRP-266 |  | DS-098 | Shelton | North | F01-F13 | Replace feeder protection F01-F13, panel rewiring and DC upgrade | 2033-11-01
PRP-080 |  | DS-093 | Tewmore | South | F01-F07 | Feeder protection replacement F01-F07, new P&C panels | 2034-02-01
PRP-122 |  | DS-118 | Nashton | North | F01-F09 | Replace feeder relays F01-F09 and RTU, IEC 61850 station bus | 2034-03-01
PRP-191 |  | TS-13 | Sumburn | Central | F01-F21 | Feeder protection and control replacement F01-F21 | 2034-04-01
PRP-220 | 2 | DS-059 | Birchworth | North | F06-F11 | Stage 2: P&C panels F06-F11, decommission old building | 2034-04-01
PRP-239 | 2 | DS-050 | Sherford | Central | F08-F13 | Stage 2: feeder protection F08-F13, RTU cutover | 2034-04-01
PRP-273 |  | DS-041 | Walfield | Central | F01-F08 | Feeder protection and control replacement F01-F08 | 2034-04-01
PRP-195 |  | DS-040 | Oakby | Central | F01-F03, F06-F07 | Replace VPR-220 relays F01-F03, F06-F07, new DC system | 2034-05-01
PRP-225 |  | DS-026 | Stillhaven | North | F03-F06, F10-F12, RTU | Replace VPR-220 feeder protection F03-F06, F10-F12 and RTU | 2034-06-01
PRP-085 |  | DS-001 | Fox Falls | Central | F01-F10 | Replace feeder protection F01-F10, panel rewiring and DC upgrade | 2034-07-01
PRP-143 |  | DS-113 | Valport | North | F01-F02, F06 | Replace VPR-220 relays F01-F02, F06, new DC system | 2034-07-01
PRP-157 |  | DS-058 | Carworth | Central | F01-F09 | P&C rebuild with new control building, feeders F01-F09 | 2034-08-01
PRP-029 |  | DS-030 | Rushgate | North | F01-F02 | Replace VPR-220 relays F01-F02, new DC system | 2034-09-01
PRP-053 |  | TS-04 | Aldby | South | F01-F24 | Replace feeder protection F01-F24, panel rewiring and DC upgrade | 2034-09-01
PRP-159 | 2 | DS-078 | Stamwell | South | F10-F16 | Stage 2: replace feeder relays F10-F16 | 2034-09-01
PRP-211 |  | DS-008 | Drayley | Central | F01-F09 | Feeder protection and control replacement F01-F09 | 2034-09-01
PRP-203 | 2 | TS-15 | Quarryhaven | South | F09-F19 | Stage 2: P&C panels F09-F19, decommission old building (VPR-220 feeders F16-F19) | 2034-10-01
PRP-262 | 2 | DS-107 | Laurel Hill | Central | F07-F12 | Stage 2: replace feeder relays F07-F12 | 2034-10-01
PRP-073 |  | DS-077 | Holbrook | Central | F01-F05 | Feeder protection replacement F01-F05, new P&C panels | 2034-11-01
PRP-111 |  | TS-09 | Stanby | Central | F01-F21 | Feeder protection and control replacement F01-F21 | 2034-11-01
PRP-065 |  | DS-034 | Rainbury | South | F01-F12 | Replace feeder protection F01-F12, panel rewiring and DC upgrade (VPR-220 feeders F09-F12) | 2035-01-01
PRP-076 |  | DS-033 | Merewood | North | F01-F09 | Replace feeder relays F01-F09 and RTU, IEC 61850 station bus | 2035-02-01
PRP-152 | 2 | TS-10 | Ravenport | South | F08-F16 | Stage 2: P&C panels F08-F16, decommission old building | 2035-04-01
PRP-028 |  | DS-023 | Ryeworth | North | F01-F10 | P&C rebuild with new control building, feeders F01-F10 | 2035-05-01
PRP-047 | 2 | TS-08 | Cran Junction | North | F13-F23 | Stage 2: P&C panels F13-F23, decommission old building | 2035-05-01
PRP-119 |  | DS-122 | Falworth | Central | F01-F10 | Feeder protection replacement F01-F10, new P&C panels | 2035-05-01
PRP-138 |  | DS-013 | Elkside | Central | F01-F10 | Replace feeder relays F01-F10 and RTU, IEC 61850 station bus | 2035-05-01
PRP-128 |  | DS-052 | Heron Junction | South | F01-F04 | Replace feeder protection F01-F04, panel rewiring and DC upgrade | 2035-06-01
PRP-153 |  | DS-061 | Hazelford | Central | F01-F16 | Replace feeder protection F01-F16, panel rewiring and DC upgrade (VPR-220 feeders F15-F16) | 2035-06-01
PRP-116 |  | DS-018 | Bram Hill | Central | F01-F08 | Feeder protection replacement F01-F08, new P&C panels | 2035-07-01
PRP-198 |  | DS-105 | Marl Falls | North | F01-F10 | Replace feeder relays F01-F10 and RTU, IEC 61850 station bus | 2035-08-01
PRP-051 | 2 | TS-01 | Barrow Junction | North | F09-F17 | Stage 2: replace feeder relays F09-F17 | 2035-09-01
PRP-136 | 2 | TS-05 | Kirkcliff | Central | F12-F22 | Stage 2: replace feeder relays F12-F22 | 2035-09-01
PRP-078 |  | DS-079 | Briarhaven | North | F01-F09 | Replace feeder protection F01-F09, panel rewiring and DC upgrade | 2035-10-01
PRP-146 |  | DS-116 | Spruceburn | North | F04, RTU | Replace VPR-220 feeder protection F04 and RTU | 2035-10-01
PRP-232 | 2 | DS-015 | Mapleham | South | F05-F11 | Stage 2: feeder protection F05-F11, RTU cutover | 2035-11-01
PRP-022 |  | DS-104 | Garhurst | Central | F01-F11 | Feeder protection replacement F01-F11, new P&C panels (VPR-220 feeders F09-F11) | Not in program period
PRP-229 |  | DS-112 | Brock Junction | Central | F01-F08 | P&C rebuild with new control building, feeders F01-F08 | Not in program period
|  | DS-021 | Collham | North | F01-F16 | Replace feeder relays F01-F16 and RTU, IEC 61850 station bus | Not in program period
|  | DS-031 | Cedar Junction | North | F01-F02 | Replace VPR-220 relays F01-F02, new DC system | Not in program period
|  | DS-032 | Neycroft | Central | F01-F06 | Replace feeder protection F01-F06, panel rewiring and DC upgrade | Not in program period
|  | DS-047 | Polmount | North | F01-F09 | P&C rebuild with new control building, feeders F01-F09 | Not in program period
|  | DS-070 | Chatwell | Central | F01-F09 | Replace feeder protection F01-F09, panel rewiring and DC upgrade, spare bay F09 fitted out | Not in program period
|  | DS-073 | Hepcliff | South | F01-F15 | Replace feeder protection F01-F15, panel rewiring and DC upgrade | Not in program period
|  | DS-081 | Thorncroft | North | F03, RTU | Replace VPR-220 feeder protection F03 and RTU | Not in program period
|  | DS-097 | Plumgate | Central | F01-F08 | Replace feeder relays F01-F08 and RTU, IEC 61850 station bus | Not in program period
|  | DS-111 | Granbrook | North | F01-F12 | Replace feeder relays F01-F12 and RTU, IEC 61850 station bus (VPR-220 feeders F10-F12) | Not in program period
|  | DS-124 | Norcroft | South | F03, F07-F08, F11, RTU | VPR-220 feeder relay replacement F03, F07-F08, F11 and RTU, panel rewiring | Not in program period

## 2025 plan (superseded)
Protection Renewal Program, 2025 planning version (superseded by the approved 2026 program)
Scheme | Stage | Substation code | Substation | Region | Bays | Scope | Commissioning month
PRP-025 |  | DS-009 | Kingview | Central | F01-F11 | Replace VPR-340 feeder relays F01-F11 | 2027-01-01
PRP-041 |  | DS-014 | Bexhurst | South | F01-F04 | Replace feeder protection F01-F04, panel rewiring and DC upgrade | 2027-01-01
PRP-068 |  | DS-022 | Rose Lake | North | F01-F10 | VPR-340 feeder protection replacement F01-F10 | 2027-01-01
PRP-095 |  | DS-037 | Gold Creek | North | F01-F12 | Replace feeder protection F01-F12, new panels | 2027-01-01
PRP-104 |  | DS-054 | Silver Mills | Central | F01-F07 | VPR-340 feeder protection replacement F01-F07 | 2027-01-01
PRP-206 |  | TS-02 | Blackhaven | North | F01-F04, F06, F08-F12 | VPR-220 feeder relay replacement F01-F04, F06, F08-F12, panel rewiring | 2027-01-01
PRP-133 |  | DS-117 | Mosswell | South | F01-F08 | P&C rebuild with new control building, feeders F01-F08 | 2027-02-01
PRP-150 |  | DS-087 | Kelville | Central | F01-F09 | Feeder protection replacement F01-F09, new P&C panels | 2027-02-01
PRP-017 |  | DS-063 | Ockham | Central | F01-F08 | Replace VPR-340 feeder relays F01-F08 | 2027-03-01
PRP-243 |  | DS-082 | Stagbury | North | F01-F11 | VPR-340 feeder protection replacement F01-F11 | 2027-03-01
PRP-147 |  | DS-060 | Upmere | South | F01-F11 | Feeder relay replacement F01-F11 | 2027-04-01
PRP-183 |  | DS-016 | Mormere | South | F01-F11 | Replace feeder relays F01-F11 and RTU, IEC 61850 station bus | 2027-04-01
PRP-035 |  | DS-095 | Eldercliff | Central | F01, F04-F05, F07-F12, RTU | Replace VPR-220 relays F01, F04-F05, F07-F12 and RTU, new DC system | 2027-07-01
PRP-167 |  | DS-106 | Swanwood | South | F01-F13 | Feeder protection replacement F01-F13, new P&C panels | 2027-07-01
PRP-105 |  | DS-003 | Dalside | North | F02-F04, F06, F08, F10 | Replace VPR-220 feeder protection F02-F04, F06, F08, F10 | 2027-09-01
PRP-024 |  | DS-007 | Tamhurst | North | F01-F08 | Feeder protection replacement F01-F08, new P&C panels | 2027-10-01
PRP-280 |  | TS-11 | Yarbury | North | F01-F24 | Feeder relay replacement F01-F24 | 2027-10-01
PRP-258 |  | DS-091 | Saltley | Central | F01-F14 | Replace VPR-340 feeder relays F01-F14 | 2027-12-01
PRP-129 |  | DS-042 | Redbury | Central | F01-F09 | Feeder relay replacement F01-F09 | 2028-04-01
PRP-260 |  | DS-005 | Branville | Central | F01-F07 | Replace feeder protection F01-F07, panel rewiring and DC upgrade | 2028-04-01
PRP-272 |  | DS-120 | Belhurst | North | F01-F05 | Feeder relay replacement F01-F05 | 2028-04-01
PRP-176 |  | DS-045 | Fish Creek | North | F01-F09 | Replace feeder protection F01-F09, new panels | 2028-05-01
PRP-276 |  | DS-100 | Atherhurst | South | F01-F13 | VPR-340 feeder protection replacement F01-F13 | 2028-05-01
PRP-049 |  | DS-074 | Clayhaven | Central | F01-F10 | Replace feeder protection F01-F10, new panels | 2028-06-01
PRP-185 |  | TS-14 | Terhaven | North | F03, F07, F09-F13, F16-F19 | Replace VPR-220 feeder protection F03, F07, F09-F13, F16-F19 | 2028-06-01
PRP-156 |  | DS-027 | Burside | South | F01-F09 | Replace feeder relays F01-F09 and RTU, IEC 61850 station bus | 2028-10-01
PRP-236 |  | DS-110 | Ash Point | Central | F01-F15 | Replace VPR-340 feeder relays F01-F15 | 2028-10-01
PRP-114 |  | DS-011 | Long Falls | South | F01-F07 | Replace feeder protection F01-F07, new panels | 2028-11-01
PRP-182 |  | DS-103 | Gildale | North | F01-F08 | VPR-340 feeder protection replacement F01-F08 | 2028-12-01
PRP-268 |  | TS-12 | Wrenmere | North | F02-F05, F07-F08, F15, F18, RTU | Replace VPR-220 feeder protection F02-F05, F07-F08, F15, F18 and RTU | 2028-12-01
PRP-081 |  | DS-090 | Radby | Central | F01-F07 | Feeder relay replacement F01-F07 | 2029-02-01
PRP-141 |  | DS-119 | Greencroft | North | F01-F11 | Feeder relay replacement F01-F11 | 2029-04-01
PRP-200 |  | DS-067 | Richgate | South | F01-F09 | Replace feeder relays F01-F09 and RTU, IEC 61850 station bus | 2029-04-01
PRP-126 |  | DS-071 | Reedby | North | F01-F07 | Replace feeder relays F01-F07 and RTU, IEC 61850 station bus | 2029-05-01
PRP-213 |  | DS-092 | Alder Mills | North | F01-F12 | Feeder protection replacement F01-F12, new P&C panels | 2029-05-01
PRP-089 |  | DS-125 | Lark Mills | Central | F01-F09 | Feeder relay replacement F01-F09 | 2029-09-01
PRP-239 |  | DS-050 | Sherford | Central | F01-F13 | Replace VPR-340 feeder relays F01-F13 | 2029-10-01
PRP-107 |  | DS-039 | Owlbury | Central | F01-F10 | P&C rebuild with new control building, feeders F01-F10 | 2029-11-01
PRP-139 |  | DS-028 | Seldale | North | F01-F09 | Replace feeder protection F01-F09, new panels | 2029-11-01
PRP-242 |  | DS-072 | Lindale | Central | F01-F11 | VPR-340 feeder protection replacement F01-F11 | 2029-11-01
PRP-218 |  | DS-025 | Bradmount | South | F01-F11 | Feeder relay replacement F01-F11 | 2030-02-01
PRP-248 |  | DS-089 | Beechwood | South | F01-F11 | VPR-340 feeder protection replacement F01-F11 | 2030-03-01
PRP-097 |  | DS-053 | Greyside | South | F01-F10 | Replace feeder protection F01-F10, new panels | 2030-04-01
PRP-123 |  | DS-115 | Coldmount | South | F01-F10 | Feeder protection replacement F01-F10, new P&C panels | 2030-04-01
PRP-252 |  | DS-080 | Slatemere | Central | F01-F11 | Feeder relay replacement F01-F11 | 2030-04-01
PRP-162 |  | DS-083 | Wolfbrook | North | F01-F05 | Replace feeder relays F01-F05 and RTU, IEC 61850 station bus | 2030-05-01
PRP-169 |  | DS-121 | Midwood | South | F01-F08 | Replace VPR-340 feeder relays F01-F08 | 2030-05-01
PRP-044 |  | DS-099 | Deer Lake | Central | F02, F04-F05, F10, RTU | Replace VPR-220 relays F02, F04-F05, F10 and RTU, new DC system | 2030-06-01
PRP-088 |  | DS-057 | Amber Mills | South | F01-F09 | Replace feeder relays F01-F09 and RTU, IEC 61850 station bus | 2030-07-01
PRP-099 |  | DS-024 | Fern Falls | North | F01-F10 | Replace feeder protection F01-F10, panel rewiring and DC upgrade | 2030-07-01
PRP-046 |  | DS-019 | Winstead | Central | F01-F07 | VPR-340 feeder protection replacement F01-F07 | 2030-10-01
PRP-201 |  | DS-069 | Arrowmount | North | F01-F05 | Feeder protection replacement F01-F05, new P&C panels | 2030-10-01
PRP-057 |  | DS-076 | Penville | South | F01-F05 | Feeder protection and control replacement F01-F05 | 2030-11-01
PRP-102 |  | TS-17 | Bellfield | South | F01-F34 | Replace feeder protection F01-F34, new panels | 2030-12-01
PRP-245 |  | DS-101 | Wargate | Central | F01-F07 | VPR-340 feeder protection replacement F01-F07 | 2031-01-01
PRP-227 |  | DS-017 | Wilbrook | Central | F01-F07 | Replace feeder protection F01-F07, new panels | 2031-03-01
PRP-034 |  | DS-044 | Otterworth | South | F01-F09 | Feeder protection and control replacement F01-F09 | 2031-04-01
PRP-171 |  | TS-07 | Rockhurst | North | F01-F03, F05-F07, F09-F12 | Replace VPR-220 feeder protection F01-F03, F05-F07, F09-F12 | 2031-04-01
PRP-117 |  | DS-064 | Whitmere | Central | F01-F10 | Replace feeder relays F01-F10 and RTU, IEC 61850 station bus | 2031-05-01
PRP-173 |  | DS-055 | Wendmore | South | F01-F04, F06-F07, RTU | VPR-220 feeder relay replacement F01-F04, F06-F07 and RTU, panel rewiring | 2031-05-01
PRP-215 |  | DS-043 | Flintdale | North | F01, F07 | VPR-220 feeder relay replacement F01, F07, panel rewiring | 2031-06-01
PRP-193 |  | DS-051 | Pine Mills | North | F05 | Replace VPR-220 feeder protection F05 | 2031-07-01
PRP-255 |  | DS-065 | Hollydale | North | F01-F07 | Replace feeder protection F01-F07, new panels | 2031-07-01
PRP-094 |  | DS-094 | Lynville | South | F01-F08 | Replace feeder relays F01-F08 and RTU, IEC 61850 station bus | 2031-08-01
PRP-262 |  | DS-107 | Laurel Hill | Central | F01-F12 | P&C rebuild with new control building, feeders F01-F12 | 2031-08-01
PRP-190 |  | DS-046 | Heathview | Central | F01-F10 | Feeder relay replacement F01-F10 | 2031-09-01
PRP-152 |  | TS-10 | Ravenport | South | F01-F16 | Replace feeder protection F01-F16, new panels | 2031-10-01
PRP-210 |  | DS-085 | Weldale | Central | F01-F05 | P&C rebuild with new control building, feeders F01-F05 | 2031-10-01
PRP-063 |  | DS-084 | Sand Junction | Central | F01-F08 | Replace feeder protection F01-F08, new panels | 2031-11-01
PRP-224 |  | DS-086 | Balbrook | North | F01-F12 | VPR-340 feeder protection replacement F01-F12 | 2031-11-01
PRP-011 |  | DS-035 | Corn River | North | F01, F03-F05, F07-F08, RTU | VPR-220 feeder relay replacement F01, F03-F05, F07-F08 and RTU, panel rewiring | 2032-04-01
PRP-083 |  | DS-066 | Harton | Central | F01-F08 | Feeder relay replacement F01-F08 | 2032-04-01
PRP-037 |  | DS-004 | Highview | North | F01-F09 | Replace feeder protection F01-F09, panel rewiring and DC upgrade | 2032-05-01
PRP-203 |  | TS-15 | Quarryhaven | South | F01-F15 | Replace VPR-340 feeder relays F01-F15 | 2032-05-01
PRP-165 |  | DS-108 | Kilwood | South | F01-F08 | Replace VPR-340 feeder relays F01-F08 | 2032-06-01
PRP-222 |  | DS-029 | Loxside | South | F01-F10 | Replace VPR-340 feeder relays F01-F10 | 2032-06-01
PRP-076 |  | DS-033 | Merewood | North | F01-F09 | Feeder relay replacement F01-F09 | 2032-09-01
PRP-163 |  | DS-068 | Fairwell | North | F01-F10 | Replace feeder protection F01-F10, new panels | 2032-10-01
PRP-232 |  | DS-015 | Mapleham | South | F01-F11 | Replace feeder protection F01-F11, new panels | 2032-10-01
PRP-014 |  | DS-096 | Camden Hill | North | F01-F10 | VPR-340 feeder protection replacement F01-F10 | 2032-11-01
PRP-132 |  | DS-010 | Elmwell | North | F01-F02 | Replace VPR-220 feeder protection F01-F02 | 2032-11-01
PRP-159 |  | DS-078 | Stamwell | South | F01-F16 | Replace VPR-340 feeder relays F01-F16 | 2032-11-01
PRP-220 |  | DS-059 | Birchworth | North | F01-F11 | Feeder protection replacement F01-F11, new P&C panels | 2032-11-01
PRP-270 |  | DS-062 | Aspenside | South | F02-F05 | Replace VPR-220 feeder protection F02-F05 | 2032-11-01
PRP-128 |  | DS-052 | Heron Junction | South | F01-F04 | Feeder relay replacement F01-F04 | 2033-02-01
PRP-047 |  | TS-08 | Cran Junction | North | F01-F23 | Replace feeder relays F01-F23 and RTU, IEC 61850 station bus | 2033-03-01
PRP-071 |  | TS-03 | Ranburn | Central | F01-F15 | Replace feeder protection F01-F15, panel rewiring and DC upgrade | 2033-03-01
PRP-109 |  | DS-038 | Stoneham | Central | F01-F11 | Replace VPR-340 feeder relays F01-F11 | 2033-03-01
PRP-278 |  | DS-102 | Calton | Central | F01-F10 | Replace VPR-340 feeder relays F01-F10 | 2033-03-01
PRP-059 |  | DS-049 | Malbrook | North | F01-F13 | VPR-340 feeder protection replacement F01-F13 | 2033-04-01
PRP-136 |  | TS-05 | Kirkcliff | Central | F01-F22 | Replace feeder protection F01-F22, panel rewiring and DC upgrade | 2033-04-01
PRP-051 |  | TS-01 | Barrow Junction | North | F01-F17 | VPR-340 feeder protection replacement F01-F17 | 2033-05-01
PRP-179 |  | DS-006 | Crowmere | Central | F01-F10 | Replace feeder protection F01-F10, new panels | 2033-06-01
PRP-263 |  | DS-114 | Kettleview | South | F01-F08 | VPR-340 feeder protection replacement F01-F08 | 2033-06-01
PRP-053 |  | TS-04 | Aldby | South | F01-F24 | Replace feeder protection F01-F24, panel rewiring and DC upgrade | 2033-07-01
PRP-022 |  | DS-104 | Garhurst | Central | F01-F08 | Replace VPR-340 feeder relays F01-F08 | 2033-09-01
PRP-138 |  | DS-013 | Elkside | Central | F01-F10 | Replace feeder relays F01-F10 and RTU, IEC 61850 station bus | 2033-09-01
PRP-229 |  | DS-112 | Brock Junction | Central | F01-F08 | VPR-340 feeder protection replacement F01-F08 | 2033-09-01
PRP-237 |  | DS-056 | Sableburn | Central | F01-F07 | Replace VPR-340 feeder relays F01-F07 | 2033-09-01
PRP-039 |  | DS-048 | Oxby | South | F01-F10 | Replace VPR-340 feeder relays F01-F10 | 2033-11-01
PRP-143 |  | DS-113 | Valport | North | F01-F02, F06 | Replace VPR-220 relays F01-F02, F06, new DC system | 2033-11-01
PRP-225 |  | DS-026 | Stillhaven | North | F03-F06, F10-F12, RTU | Replace VPR-220 feeder protection F03-F06, F10-F12 and RTU | 2033-11-01
PRP-234 |  | DS-075 | Edgecliff | North | F01-F09 | Feeder protection replacement F01-F09, new P&C panels | 2033-11-01
PRP-266 |  | DS-098 | Shelton | North | F01-F13 | VPR-340 feeder protection replacement F01-F13 | 2033-11-01
PRP-080 |  | DS-093 | Tewmore | South | F01-F07 | VPR-340 feeder protection replacement F01-F07 | 2034-02-01
PRP-111 |  | TS-09 | Stanby | Central | F01-F21 | Feeder protection and control replacement F01-F21 | 2034-02-01
PRP-122 |  | DS-118 | Nashton | North | F01-F09 | Feeder relay replacement F01-F09 | 2034-03-01
PRP-191 |  | TS-13 | Sumburn | Central | F01-F21 | Feeder protection and control replacement F01-F21 | 2034-04-01
PRP-273 |  | DS-041 | Walfield | Central | F01-F08 | Replace feeder protection F01-F08, new panels | 2034-04-01
PRP-195 |  | DS-040 | Oakby | Central | F01-F03, F06-F07 | Replace VPR-220 relays F01-F03, F06-F07, new DC system | 2034-05-01
PRP-085 |  | DS-001 | Fox Falls | Central | F01-F10 | Replace feeder protection F01-F10, panel rewiring and DC upgrade | 2034-07-01
PRP-157 |  | DS-058 | Carworth | Central | F01-F09 | P&C rebuild with new control building, feeders F01-F09 | 2034-08-01
PRP-211 |  | DS-008 | Drayley | Central | F01-F09 | Feeder protection and control replacement F01-F09 | 2034-09-01
PRP-073 |  | DS-077 | Holbrook | Central | F01-F05 | Feeder relay replacement F01-F05 | 2034-11-01
PRP-065 |  | DS-034 | Rainbury | South | F01-F08 | VPR-340 feeder protection replacement F01-F08 | 2035-01-01
PRP-028 |  | DS-023 | Ryeworth | North | F01-F10 | P&C rebuild with new control building, feeders F01-F10 | 2035-05-01
PRP-119 |  | DS-122 | Falworth | Central | F01-F10 | Replace VPR-340 feeder relays F01-F10 | 2035-05-01
PRP-153 |  | DS-061 | Hazelford | Central | F01-F14 | VPR-340 feeder protection replacement F01-F14 | 2035-06-01
PRP-116 |  | DS-018 | Bram Hill | Central | F01-F08 | Replace VPR-340 feeder relays F01-F08 | 2035-07-01
PRP-198 |  | DS-105 | Marl Falls | North | F01-F10 | Replace feeder protection F01-F10, new panels | 2035-08-01
PRP-078 |  | DS-079 | Briarhaven | North | F01-F09 | VPR-340 feeder protection replacement F01-F09 | 2035-10-01
PRP-146 |  | DS-116 | Spruceburn | North | F04, RTU | Replace VPR-220 feeder protection F04 and RTU | 2035-10-01

## Notes
Program management notes, P&C Asset Planning. The program is approved by the Board each March with the capital budget; the approved version replaces the planning version of the year before.
Funding: P&C renewal line of the capital plan. A scheme is released to detailed design about eighteen months before its commissioning month, and its material is ordered at release.
Outage windows: most commissioning is planned in the spring (April to June) and autumn (September to November) windows, clear of the summer and winter peaks. Winter work is limited to stations with a full back-feed.
Staging: large stations are rebuilt in two outage stages, so that half the feeders stay on the existing protection while the other half is cut over. Each stage replaces the bays it lists.
Commissioning month: the month the new protection for the listed bays is commissioned. The relays in a commissioned bay are out of service from the first day of the commissioning month.
Bays: a scheme lists every feeder bay its new panels serve, including spare bays and feeders on other relay types at the same station.
Scheme numbers are assigned when a scheme first enters the program and do not change between versions. RTU-only schemes moved to the SCADA upgrade program in 2026 are no longer listed here.
Stations rebuilt under the 2022-2025 station renewals are complete and are not listed.
Schedule questions: Kurt Allison, Senior Asset Engineer, P&C.